## User stories
| Main User Story | Sub-Task
1 | SoftBridge Database | Create Product Table to Store data
2 | SoftBridgeAPI | Create Model from Database First approach
Get,Post and Delete Methods of API
3 | SoftBridge Application | Create Page with Add Form and List
Details of Product
4 | Unit Test | SoftBridge API Unit Test case
SoftBridge APP Unit Test case

## Tracker
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day
1 | SoftBridge Database
1.1 | Create table SoftBridgeProduct | 1 | 0.5 | Day1
1.2 | SoftBridgeAPI |  |  | Day1
1.2.1 | Create Model from Database First approach | 0.5 | 0.5 | Day1
1.2.2 | Create Get, Post & Delete Methods | 2 | 2 | Day1
1.2.3 | Exception Handling | 2 | 1.5 | Day2
1.3 | SoftBridge Application
1.3.1 | Create Product Model | 0.5 | 0.5 | Day2
1.3.2 | Create Product Controller for Get All Details | 0.5 | 0.5 | Day2
1.3.3 | Create Product Controller for Product Detail by ID | 0.5 | 0.5 | Day2
1.3.4 | Create Product Controller for Post All Details | 1 | 1 | Day2
1.3.5 | Create Product Controller for Delete Detail by ID | 0.5 | 0.5 | Day2
1.3.6 | Create View for Add Product and list of Product | 2 | 2 | Day3
1.3.7 | Create View for details of product | 1 | 1 | Day3
1.3.8 | Exception Handling | 2 | 1.5 | Day3
1.4 | Unit Test
1.4.1 | Unit Test SoftBridgeAPI | 2 | 2 | Day3
1.4.2 | Unit Test SoftBridge APP | 3 | 3 | Day3